|  |  |  |  |
| --- | --- | --- | --- |
| **Risks** | **Impact** | **Risk Level** | **Mitigation Strategy** |
| Failure to receive the required appropriation as a result of the presentation made to the municipalities | High | Medium | Re-preparing and presenting the project in detail or finding sponsors for the project |
| Housewife/househusbands' inability to attend trainings due to problems of not leaving the house | High | High | Providing online training option for participants who do not have the opportunity to participate physically |
| Emergence of material-related problems in greenhouse construction | High | Medium | Making a comprehensive agreement with the construction company to provide material and operational control |
| Not being able to go to the fairs held abroad as a result of the closure of overseas exits due to the pandemic etc. | Medium | Low | To participate in fairs online |

|  |  |  |
| --- | --- | --- |
| Assumption | Probability | Description |
| Approval for the project was received and necessary financial support received | High | You need this to be true for implementing the project |
| The project became known as a result of the advertisements made to announce the project | High | You need this to be true for implementing the project |
| The expected participation in the project was achieved and the training was productive | High | You need this to be true for implementing the project |
| Cafes and similar venues in the city were willing to participate in the project | High | You need this to be true for implementing the project |
| The greenhouse construction was completed without any problems and the work continued with volunteers | High | You need this to be true for implementing the project |
| Determined groups participated in international fairs, their knowledge on the subject increased | High | This would be beneficial for the project |
| The project was successful in the province of Ankara and spread to other provinces | High | You need this to be true for implementing the project |
| 1 year training was given to the participants | High | You need this to be true for implementing the project |