## Sheet1
Activity /Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Implementing Party | Activity /Months | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | Implementing Party
Activity No 1.1: Applying for constitutional arrangements to the Ministry of Justice | [12 empty] | Ministry of Justice | Activity No 1.1: Applying for constitutional arrangements to the Ministry of Justice | [12 empty] | Ministry of Justice
Activity 1.2: Meetings for increasing investments on recycling centers | [12 empty] | Relative institutions, organizations, and ministries | Activity 1.2: Meetings for increasing investments on recycling centers | [12 empty] | Relative institutions, organizations, and ministries
Activity No 1.3: Meetings for increasing investments on recycling greenhouses | [12 empty] | Relative institutions, organizations, and ministries | Activity No 1.3: Meetings for increasing investments on recycling greenhouses | [12 empty] | Relative institutions, organizations, and ministries
Activity No 1.4: Presenting reports to Ministry of Environment and Urbanization about harms of domestic wastes | [12 empty] | Ministry of Environment and Urbanization and Municipalities | Activity No 1.4: Presenting reports to Ministry of Environment and Urbanization about harms of domestic wastes | [12 empty] | Ministry of Environment and Urbanization and Municipalities
Activity No1.5: Applying to Ministry of National Education and metropolitan municipalities for opening education centers about recycling | [12 empty] | Ministry of National Education and Municipalities | Activity No1.5: Applying to Ministry of National Education and metropolitan municipalities for opening education centers about recycling | [12 empty] | Ministry of National Education and Municipalities
Activity No 2.1: Starting education about how recycle domestic waste on metropolitans | [12 empty] | Metropolitan Municipalities | Activity No 2.1: Starting education about how recycle domestic waste on metropolitans | [12 empty] | Metropolitan Municipalities
Activity No 2.2: Starting education about how recycle domestic waste on cities other than meropolitans | [12 empty] | Municipalities other than metropolitans | Activity No 2.2: Starting education about how recycle domestic waste on cities other than meropolitans | [12 empty] | Municipalities other than metropolitans
Activity No 2.3: Education about how to tranforms recycling into financial support opportunity | [12 empty] | Ministry of National Education and Municipalities | Activity No 2.3: Education about how to tranforms recycling into financial support opportunity | [12 empty] | Ministry of National Education and Municipalities
Activity No 2.4: Getting necessary permissions from the General Directorate of Copyrights to be able to give sertificates to who attend the trainings | [12 empty] | Ministry of National Education and General Directorate of Copyrights | Activity No 2.4: Getting necessary permissions from the General Directorate of Copyrights to be able to give sertificates to who attend the trainings | [12 empty] | Ministry of National Education and General Directorate of Copyrights
Activity No 3.1: Preparing informative brochures to facilitate the process | [12 empty] | Promoters | Activity No 3.1: Preparing informative brochures to facilitate the process | [12 empty] | Promoters
Activity No 3.2: Preparing short informative videos on public transportations about recycling | [12 empty] | Promoters and Municipalities | Activity No 3.2: Preparing short informative videos on public transportations about recycling | [12 empty] | Promoters and Municipalities
Activity No 3.3: Preparing billboard posters for spreading awareness on recycling | [12 empty] | Promoters and Municipalities | Activity No 3.3: Preparing billboard posters for spreading awareness on recycling | [12 empty] | Promoters and Municipalities
Activity No 3.4: Sending sertificated participants from metropolitans abroad to learn about recycling on different countries | [12 empty] | Ministry of National Education, Ministry of Environment and Urbanization, and Promoters | Activity No 3.4: Sending sertificated participants from metropolitans abroad to learn about recycling on different countries | [12 empty] | Ministry of National Education, Ministry of Environment and Urbanization, and Promoters
Activity No 3.5: Spreading recycling greenhouses around the country | [12 empty] | Ministry of Environment and Urbanization and Investors | Activity No 3.5: Spreading recycling greenhouses around the country | [12 empty] | Ministry of Environment and Urbanization and Investors